GI 00126

SITE ACTIVITY PLAN FOR PROJECTS CONTAINING

GREEN INFRASTRUCTURE FACILITIES

GI 00126.00 Purpose of the Special Provision.

- GI 00126 – Site Activity Plan for Projects Containing Green Infrastructure (GI) Facilities is intended to demonstrate that the contractor understands the contract documents and has thoroughly planned sequencing, site preparation, installation, and establishment of green infrastructure facilities. The Site Activity Plan shall be submitted and approved prior to commencement of any field activities.

GI 00126.01 Description.

- This special provision includes the requirements for development of a Site Activity Plan for Green Infrastructure Facilities. A Site Activity Plan is a collection of illustrated plans which identify a detailed construction schedule, addresses stormwater runoff during construction, summarizes means of access to the site, and identifies the anticipated site utilization. The Contractor may combine the components listed in Table so long as the information required of all components is clearly defined. The Contractor is responsible for developing a Site Activity Plan and maintaining up-to-date documents throughout the project lifecycle.

Table 1: Site Activity Plan Components

| Site Activity Plan Component | Description | References |
| --- | --- | --- |
| Construction Schedule | Green Infrastructure sequencing and phasing activities incorporated into the Construction Progress Schedule | NO DPW C126 SP 00126.02 |
| Runoff Management Plan for construction of GI Facilities | Plan sheet and notes illustrating Contractor’s understanding and compliance with SP 00126.03 | NO DPW C204 SP 00126.03 |
| Site Access Plan | Plan sheet and notes illustrating Contractor’s understanding and compliance with SP 00126.04 | NO DPW C125 NO DPW C128.04 NO DPW C129 NO DPW C130 NO DPW C131 NO DPW C204 NO DPW C402 NO DPW C713 SP 00126.04 SP 00200 |
| Site Utilization Plan | Plan sheet and notes illustrating Contractor’s understanding and compliance with SP 00126.05 | NO DPW C125 NO DPW C130 NO DPW C131 NO DPW C204 NO DPW C402 SP 00126.05 SP 00718 |

GI 00126.02 Construction Schedule.

- Description. A construction progress schedule, in accordance with NO DPW C126.01 which includes critical green infrastructure sequencing and phasing tasks necessary to ensure the protection and performance of green infrastructure facilities.

- Applicable Standards

- NO DPW C126: Performance of Work

- Execution: The Contractor shall include additional activities within the construction progress schedule outlining project-wide green infrastructure-related sequencing and phasing necessary to comply with the contract documents. Specifically, the Contractor shall include the following schedule activities:

- Procurement of green infrastructure materials including planting materials, lead times, and any storage requirements

- Installation and completion of GI components (excavation, underdrain installation, backfill placement, setting bed installation, joint fill installation, bioretention soil placement, mulch placement, planting, etc. as applicable)

- Diversion of flow

- Plant establishment including monthly site inspection and maintenance activities

- Site stabilization activities including stabilization of areas upstream of any green infrastructure.

GI 00126.03 Runoff Management Plan for Construction of GI Facilities.

- Description. The work specified in this Section consists of providing, maintaining and removing temporary erosion and sedimentation controls as necessary during construction of GI facilities.

- Applicable Standards: NO DPW C204: Environmental Protection and Stormwater Pollution Prevention Plan

- Execution: The Site Activity Plan shall outline the Contractor’s approach to runoff management and the protection of green infrastructure facilities prior to, during, and following construction. The illustrated plan shall be developed in accordance with the following:

- Erosion and sediment control intended to protect GI shall be provided, installed, and maintained per NO DPW C204.

- Unless approved by the project Designer, proposed green infrastructure facilities shall not be used for collection or conveyance of stormwater during construction or until site is stabilized and commissioning of green infrastructure facility is approved by Owner.

- Any sedimentation occurring in the footprint of proposed green infrastructure during construction shall be promptly removed by the contractor. Contractor shall re-scarify the green infrastructure excavation following sediment removal to the satisfaction of the project Designer prior to placement of aggregate or bioretention soil.

- Underdrain piping, aggregates and soils, and pervious paving shall not be installed until contributing drainage areas are stabilized to the satisfaction of the Designer. Any discharge of sediment that affects the performance of the underdrain or green infrastructure facility shall be corrected to restore hydraulic performance.

- Runoff shall not be allowed to discharge into a completed green infrastructure facility until authorized by the Designer.

GI 00126.04 Site Access Plan.

- Description. The work specified in this Section consists of providing and maintaining site access as necessary for construction of green infrastructure facilities while protecting the green infrastructure facilities from construction related compaction, sedimentation, or other negative effects on the long-term performance of the facility. The Site Access Plan shall address site access, haul roads, delivery of materials, and any temporary facilities such as temporary nurseries and storage of materials.

- Applicable Standards

- NO DPW C125: Public Convenience

- NO DPW C128.04: Required Traffic Provisions

- NO DPW C129: Temporary Signs, Barricades, Pavement Markings, Construction Signing, Traffic Maintenance, and Public Safety

- NO DPW C130: Materials, Equipment, Employees, Contractor Quality Control

- NO DPW C131: Removal of Improper Material

- NO DPW C204: Environmental Protection and Stormwater Pollution Prevention Plan

- NO DPW C402: Traffic Maintenance Aggregate

- NO DPW C713: Temporary Signs, Barricades, and Pavement Markings

- GI 00200: Earthwork for Green Infrastructure Facilities

- LaDOTD Louisiana Standard Specifications for Roads and Bridges, Latest Edition

- MUTCD: Manual on Uniform Traffic Control Devices

- Execution

- Site Access:

The Site Access plan shall illustrate how non-construction related pedestrian, bicycle, and vehicular access will be maintained to and around the site throughout the duration of the project.

The Site Access Plan shall illustrate how construction related vehicular and equipment access, material delivery and storage, and execution of construction activity will be maintained to, around, and within the project site throughout the duration of the project.

In accordance with NO DPW C713.01: Maintenance of Traffic, access to the construction site cannot interfere with access to all property adjacent to the site.

- Haul Roads:

The Site Access Plan shall include a map showing the intended haul roads to be used for heavy and large equipment access to the site. The City shall review and approve the proposed haul roads prior to construction commencing. If revisions are made to the haul roads, the Contractor shall revise the haul road map in the Site Access Plan.

Permanent roads installed with permeable pavements or pavers shall not be used for haul roads.

The Contractor shall adhere to the all legal load restrictions as indicated in NO DPW C503.04.

For haul roads that must be located within the footprint of a proposed green infrastructure facility or component, the Site Access Plan shall include Contractor’s plans for de-compaction of the site in accordance with the procedures contained in GI 00200, or removal and replacement of any soils not planned for excavation.

- Transportation and Delivery of Materials

The Site Access plan shall include a description and/or map of material delivery and storage procedures and locations. The plan shall indicate the means of access to the site for delivery of materials.

Storage and Handling of Materials shall be in accordance with appropriate section in Specifications.

GI 00126.05 Site Utilization Plan.

- Description. The work specified in this Section consists of protecting green infrastructure facilities from construction traffic, material delivery and storage, and erosion/sedimentation caused by typical construction activity.

- Applicable Standards

- NO DPW C125: Public Convenience

- NO DPW C130: Materials, Equipment, Employees, Contractor Quality Control

- NO DPW C131: Removal of Improper Material

- NO DPW C204: Environmental Protection and Stormwater Pollution Prevention Plan

- NO DPW C402: Traffic Maintenance Aggregate

- Execution: The Site Utilization Plan shall include:

- A description of the open excavation protection that will be employed

- A description of how private property will be protected

- A description of how trees and vegetation will be protected and a map showing trees and vegetation to receive protection

- A description of how existing structures and utilities will be protected

- A description of how flow in sewers, drains, and water courses will be maintained during the progress of the work

- A map showing the location of anticipated material storage, laydown areas, and temporary facilities

- A description of how stored materials will be protected during the course of the work

- A description of methods for disposal of materials

- A description of the equipment and methods used to backfill with specified materials in a manner that does not compact the subgrade or backfill materials of green infrastructure facilities.

GI 00126.06 Measurement.

The cost for development of the Site Activity Plan shall be spread among the various bid items associated with the construction of the GI Facility.

All specific items and activities documented in the Site Activity Plan shall be measured as indicated in other applicable special provisions.